## Sheet1
Task | Date Added | Status | Date Completed | ETC Things
fix radar positions | 2017-06-17 | DONE | N/A
fix radar colour | 2017-06-17 | DONE | N/A
fix collision box on car | 2017-06-17 | DONE | N/A
fix wheel placement on car | 2017-06-17 | DONE | N/A
fix low health - blinking cars | 2017-06-17 | DONE | N/A
make VS organized in folders again | 2017-06-18 | DONE | N/A
traps more projectile | 2017-06-18 | DONE | N/A
font and armour fonts larger for game hud | 2017-06-18 | DONE | N/A
Different game modes in title screen | 2017-07-05 | DONE | N/A
fix crash of game mode index in title screen | 2017-07-05 | DONE | N/A
Get timer mode working - have game loop end when timer ends | 2017-07-07 | DONE | N/A
sfx for throwing traps | 2017-07-08 | DONE | N/A
check if vehicle is human and only play sfx for human cars | 2017-07-12 | DONE | N/A
sfx for getting health and armour | 2017-07-08 | DONE | N/A
Transfer DODO txt document to Excel sheet | 2017-07-11 | DONE | N/A
Fix Audio.cpp and arrange channels for various sfx (enum) | 2017-07-12 | DONE | N/A
speed up some of the sfx | 2017-07-12 | DONE | N/A
RulesScreen | 2017-07-19 | DONE | N/A
MainScreen | 2017-07-19 | DONE | N/A
MultiplayerScreen | 2017-07-19 | DONE | N/A
CarScreen | 2017-07-19 | DONE | N/A
Arena Screen | 2017-07-19 | DONE | N/A | Don't need anymore
Mode Screen | 2017-07-19 | DONE | N/A
Skybox Screen | 2017-07-22 | DONE | N/A | Don't need anymore | DONE
Fix updateGameText | 2017-07-24 | DONE | N/A
TitleScreen - fix mesh rendering | 2017-07-24 | DONE | N/A | DONE
TitleScreen - fix skybox rendering | 2017-07-24 | DONE | N/A | DONE
TitleScreen - fix placement of mesh and skybox choice | 2017-07-24 | DONE | N/A | TODO: update controls/have controls blinking on bottom of screen or something | DONE
For title screens, update positions and cooler background | 2017-07-22 | DONE | n/a
Timer mode | 2017-07-08 | Essentially done
Sudden death mode | 2017-07-08 | Essentially done
timer and sudden death mode in game - use interfaces | 2017-06-17 | in progress
Fix code -> make better and less awful | 2017-07-17 | In progress
Make title screen code better ->interfaces? | 2017-07-17 | Essentially done | 2017-07-26 | Essentially done
TitleScreen.cpp - make better now that other Screens are done | 2017-07-22 | Essentially done | 2017-07-26 | Main parts done, just fiddling
TItleScreen - fix camera | 2017-07-24 | Essentially done | 2017-07-26 | Fiddling
Movie playing in title screen | 2017-06-17 | Cancelled | n/a | Decided against; did something different
Shadows | 2017-06-17
arena culling | 2017-06-17
different music for different levels | 2017-06-17
armour and health - bars instead of numbers (or both) | 2017-06-17
fix colour when dead | 2017-06-18
TIME OVER message instead of RETIRE in timer mode | 2017-07-08
update rules screen and controls | 2017-07-08
Config file for variables | 2017-07-17
Create parser for config file | 2017-07-17
CarScreen - fix the "Player X…. " text so that doesn't switch when done | 2017-07-25 | DONE | 2017-07-26
TitleScreen - "PLAY" button before going to start of game? | 2017-07-25 | DONE | N/A
TitleScreen - fix colour of text, black sort of hard to see | 2017-07-25 | DONE | 2017-07-26 | Still messing around with variables, but main part done
Fix pause menu-update it | 2017-07-25