## Sheet1
Task | Date Added | Status |  | ETC Things
Movie playing in title screen | 2017-06-17 |  |  | Put back to fullscreen once done
Shadows | 2017-06-17
timer and sudden death mode in game - use interfaces | 2017-06-17 | in progress
arena culling | 2017-06-17
different music for different levels | 2017-06-17
fix radar positions | 2017-06-17 | DONE
fix radar colour | 2017-06-17 | DONE
fix collision box on car | 2017-06-17 | DONE
fix wheel placement on car | 2017-06-17 | DONE
armour and health - bars instead of numbers (or both) | 2017-06-17
fix low health - blinking cars | 2017-06-17 | DONE
make VS organized in folders again | 2017-06-18 | DONE
traps more projectile | 2017-06-18 | DONE
fix colour when dead | 2017-06-18
font and armour fonts larger for game hud | 2017-06-18 | DONE
Different game modes in title screen | 2017-07-05 | DONE
fix crash of game mode index in title screen | 2017-07-05 | DONE
Get timer mode working - have game loop end when timer ends | 2017-07-07 | DONE
Timer mode | 2017-07-08 | Essentially done
Sudden death mode | 2017-07-08 | Essentially done
TIME OVER message instead of RETIRE in timer mode | 2017-07-08
sfx for throwing traps | 2017-07-08 | DONE
check if vehicle is human and only play sfx for human cars | 2017-07-12 | DONE
sfx for getting health and armour | 2017-07-08 | DONE
update rules screen and controls | 2017-07-08
Transfer DODO txt document to Excel sheet | 2017-07-11 | DONE
Fix Audio.cpp and arrange channels for various sfx (enum) | 2017-07-12 | DONE
speed up some of the sfx | 2017-07-12 | DONE
Fix code -> make better and less awful | 2017-07-17 | In progress
Make title screen code better ->interfaces? | 2017-07-17 | In Progress
Config file for variables | 2017-07-17
Create parser for config file | 2017-07-17
RulesScreen | 2017-07-19 | DONE
MainScreen | 2017-07-19 | DONE
MultiplayerScreen | 2017-07-19 | DONE
CarScreen | 2017-07-19 | DONE
Arena Screen | 2017-07-19 | DONE
Mode Screen | 2017-07-19 | DONE
Skybox Screen | 2017-07-22 | DONE | Get textures showing up
For title screens, update positions and cooler background | 2017-07-22 | Done positions
TitleScreen.cpp - make better now that other Screens are done | 2017-07-22 | In progress
Fix updateGameText | 2017-07-24 | DONE
TitleScreen - fix mesh rendering | 2017-07-24
TitleScreen - fix skybox rendering | 2017-07-24
TitleScreen - fix placement of mesh and skybox choice | 2017-07-24
TItleScreen - fix camera | 2017-07-24